PPHSN-CB 10 Meeting Tentative Workplan

| INITIATIVES | DATE/TIMING | ACTIVITIES | RESPONSIBILITIES | FUNDING |
| --- | --- | --- | --- | --- |
| # LabNet development |  |  |  |  |
| Strengthening L2 labs | Starting first half 2005 | - Accreditation with measles lab network - Assessment and development plans finalised | WPRO/EPI WHO | WHO GFATM, WHO |
| Strengthening L1 labs | End August 2004 | - Assessment and development plans of 8 laboratories completed - Assessment for foodborne surveillance activities | WR SP office Foodborne WG | GFATM WHO Tb funds (for Tuvalu) WHO GSS |
| QA & QC | On-going | - Using materials fm Manila meeting Nov 03, preparing SOP manual for referral of specimens fm L1 to L2 to L3 | WHO, PPTC, SPC, RlabC (PIHOA) | US-BT? ADB (yet to be confirmed) |
| Training for lab health workers | 2005 | - Initial training - Bridging courses - L1 L2, L1L3 & L2 L3 exchange schemes - Specialised course through POLHNet | Palau AHEC, FSM, PPTC & SPC IPNC, WR SP office ? WHO, PPTC & partners | GFATM ADB (yet to be confirmed) |
| Formalising links L1 & L2 | End of 2004 | - MOUs agreed on and signed | LabNet TWB (with respective labs) | NA |
| Links with Aus PHLN | End of June 2004 – On-going | - Start participation & discussions on links at teleconferences | LabNet TWB | NA |
| Links with NZ PHLN | End 2004 | - Liase with Dr Doug Lush - Explore the feasibility of specimen referral to NZ for PH purposes | LabNet TWB | NA |
| Pilot Revolving fund in AAPI established and operational for LabNet operations | ? July 2004 Then on-going | - All funds made available - Funds used, monitored and replenished | CDC/PIHOA Epid | US-BT |

| INITIATIVES | DATE/TIMING | ACTIVITIES | RESPONSIBILITIES | FUNDING |
| --- | --- | --- | --- | --- |
| Structural & operational maintenance & reinforcement (not specific to LabNet) |  |  |  |  |
| PPHSN Revolving Fund | Mar 2005 | - Consultation - Submission for Samoa MoH meeting | RF WG | NA |
| PPHSN extension | End 2004 | - Explore inclusion of Tb (PaTLab), & EPI diseases (other than measles) | SPC & WHO | NA (funding related to respective |
|  | June 2004-June 2005 | - Include foodborne disease surveillance: working group established and tasked | FSM | workplans) |
|  | Done | - Inclusion of HIV/STIs | SPC & WHO |  |
| IHR & PPHSN | 11 June 2004 | - Identification of integration mechanisms | PPHSN-CB | NA |
|  | Before Nov 2004 | - Feedback fm MoH | SPC & EpiNet teams |  |
|  | March 2005 | - Endorsement by MoH (Samoa MoH meeting) | SPC & WHO |  |
|  | End August 2004 On-going | - Assist in IHR implementation - Country rapid assessment - Training in algorithms utilisation - In-depth assessment | SPC & WHO |  |
| RET operational as a regional response mechanism | Mid-June 2004 | - RET WG set up | PPHSN-CB | NA |
|  | End 2004 | - Draft and circulate detailed TORs, incl. budget/funding plan | RET WG |  |
|  | End 2004 | - Identification and contact information of individuals within pools of prospective core & auxiliary members | RET WG |  |
|  | End 2005 | - Compile an operation manual for the RET | RET WG |  |
|  | Mar 2005 | - Endorsement by MoH meeting in Samoa | SPC & WHO |  |
| WHO KL influenza pandemic preparedness meeting for resource-poor countries | End of June End of July | - PPHSN represented at the meeting - Feedback to PPHSN | WHO | WHO |

| Regional training in epid/PHS | End 2004 | - Training needs assessment (survey), incl. delivery modes | FSM & EpiNet teams | ? |
| --- | --- | --- | --- | --- |
|  | Jun 2005 | - Regional training strategy development | PPHSN-CB & training partners | NA |
|  | On-going | - Inter-institutional collaboration & accreditation | PPHSN-CB & training partners | NA |
|  | Sept 2004 Oct 2004 | - Training activities: - Short-course - DDM - MAE… | SPC, PIHOA PIHOA, FSMed, SPC, NCEPH… | US-BT & WHO US-BT US-BT & scholarships |
| Projects/research (details to be included in the Directory of research/surveillance projects) | Nov03-Jun05 | - Lepto survey | SPC & EpiNet team members | WHO & SPC |
|  | ? | - AF&R/DVBS/Part Agglut | WHO/SP/EPI |  |
|  | On-going | - HIV/STIs surveys | WHO & SPC | GFATM & SPC |
|  | Sep04-Dec05 | - Targeted Foodborne Disease studies | FSM/PPHSN partners | PPHSN partners |
|  | Jan05-Dec07 | - Dengue surveillance best practices | FSM/PPHSN partners | WHO TDR |
|  | On-going | - NCD surveillance | FSM/PPHSN partners | WHO & countries |
|  | Apr-Oct04 Sept 04 + | - Building ICT capacities for PHS & CD databases Exploring using emails for reporting of AFP/AFR Hospital-based active surveillance in trial countries | SPC & AAPI WHO/SP and SPC | US-BT & SPC WHO& SPC |
| Bioethics addressed | Sep 2004 | - Bioethics TWG established - TORs drafted and circulated | FSM/PHRC/PPHSN | NA |
| PPHSN-CB membership - Renewal | By Dec 2004 | - Nomination fm PNG and Polynesian subregional organised and received - At large renewal of NC seat organised and achieved - Renewal of 1 allied member in the PPHSN-CB organised and achieved | SPC | NA |

| - Status |  | - Endorsement fm FSM to be a permanent member | FSM |  |
| --- | --- | --- | --- | --- |
| Review & improve on infection control measures in PICTs | Mid of 2005 and ongoing | - Assess capacity on infection control and identify training needs in PICTs | PPHSN- (SPC/WHO) | ? SPC/WHO (other donor partners) |
|  | End of 2005 and ongoing | - Conduct some trainings {?subregional(1)/in country (3)} | PPHSN- (SPC/WHO) | ? SPC/WHO (other donor partners) |
|  | End of 2004 | - Formalise and operationalise Pacific regional infection control network (PICnet) under PPHSN umbrella. | PPHSN-CB/Focal point | NA |
|  | End of 2005 | - Develop a PPHSN Infection Control Guideline | PPHSN (SPC/WHO) | ?WHO (APW) |
| INITIATIVES | DATE/TIMING | ACTIVITIES | RESPONSIBILITIES | FUNDING |
| # Develop PPHSN information, publication and documentation |  |  |  |  |
| Finalise & publish the PPHSN guidelines | June 2004 | - Secure funding & select experts among EpiNet National Teams membership | WHO/SPC | WHO |
|  | June 2004 | - Selected EpiNet members to compile comments & finalise the draft guidelines | WHO | WHO |
|  | Sep 2004 | - Share for feedback and inputs the final draft guidelines with the EpiNet teams | SPC & EpiNet team members | N.A. |
|  | Feb 2005 | - Publication & dissemination final guidelines | SPC | SPC |
|  | Mar 2005 | - Submit the final guidelines to WHO/SPC HoH & Ministerial Meeting in Samoa for advocacy & marketing | WHO/SPC |  |
| Directory of resources | End 2004? Beginning 2005 Mid-2005 On-going | - First draft - Feedback - Final doc - Updates | SPC & PPHSN partners | SPC |

| Directory of research/surveillance projects | End 2004? Beginning 2005 Mid-2005 On-going | - First draft - Feedback - Final doc - Updates | PHRC, SPC & PPHSN partners | ? |
| --- | --- | --- | --- | --- |
| Publication of Inform’Action issues | On going | - Encourage PPHSN members contributions | CB members | N.A. |
|  |  | - Implement all other publication-related activities | SPC | SPC |
| Maintain & update the PPHSN and DE in health Website | On going | - Update on-line information | SPC/CB members | SPC |
|  |  | - Link with the PPHSN regional CD database | SPC | SPC |
| Develop/organise the PPHSN CDs regional database | Dec 2005 – On-going | - Liase with PICTs to organise data transfer and accessibility | SPC | SPC |
| Document legislative & regulatory models for CDs S&R | On going | - Collect, compile, disseminate appropriate documentation - Post on-line documentation and disseminate otherwise | SPC SPC | N.A. |

Note: Activities specific to influenza pandemic planning and guidance are not included in the above plan and will be part of the 2nd Regional EpiNet Workshop recommendations.