SECRETARIAT OF THE PACIFIC COMMUNITY

8th MEETING OF THE COORDINATING BODY (CB)

Of THE PACIFIC PUBLIC HEALTH SURVEILLANCE NETWORK (PPHSN)

24 — 26 July 2002, Noumea, New Caledonia

## Annex 1 – PPHSN 12 months Plan of Action

| INITIATIVES | DATE/TIMING | ACTIVITIES | RESPONSIBILITIES | FUNDING |
| --- | --- | --- | --- | --- |
| # PPHSN Meetings, workshops, training sessions |  |  |  |  |
| Organise a LabNet Meeting | Feb. 2003 (1st week) Suva, Fiji | - Secure funding & other resources - Identify a L2 lab for PNG - Prepare agenda - Send out invitations - Generate & compile working documents - Make all other administrative arrangements | TWB | Pending ? WHO/SPC/CDC (BioTerrorism) |
| Organise a regional EpiNet Meeting | Feb. 2003 (2nd week) Nadi/Suva, Fiji (to be explored) | - Explore the various possible options with PEHI/CDC for combining Micronesian EpiNet & regional EpiNet Meeting - Draft evaluation & monitoring guidelines for EpiNet teams (national & regional) - Model ToRs (national & regional) - Secure funding & other resources - Prepare agenda - Send out invitations - Generate & compile working documents - Make all other administrative arrangements | SPC Selected EpiNet members (ref. Guidelines) CB members WHO/SPC SPC CB members WHO/SPC | Pending ? WHO/SPC/CDC (PEHI/BT) |
| Organise a regional Consultation meeting for PPHSN training activities | Feb. 2003 Before end 2003 | - Conduct training needs analysis (separate from LabNet needs) - Secure funding & other resources - Prepare agenda - Send out invitations - Generate & compile working documents - Make all other administrative arrangements | EpiNet Meeting specific working group Fiji School of Medicine | Not Applicable ? ? |
| Conduct field investigation training in selected PICTs | Nov. 2002 Before end 2003 | - In Micronesian PICTs - In South Pacific PICTs | WHO/SPC/CB members | WHO/UNICEF WHO/UNICEF |

| # PPHSN Planning and structures’ development |  |  |  |  |
| --- | --- | --- | --- | --- |
| Prepare a flexible review & update process for EpiNet teams membership (national & regional) | Before Oct. 2002 | - Draft the procedure - Contact EpiNet National Focal Points - Identify L1 national Focal Point | SPC | N.A. |
| Develop & implement a PPHSN Strategic plan | Before Oct. 2002 | - Put together the existing PPHSN planning documentation - Refine Mission statement etc. - Devote part of the plan to fund raising strategy, advocacy and policy framework | SPC CB members CB members | N.A. |
| Consider inclusion of NCDs in PPHSN | Before end 2002 | - Prepare discussion document - Circulate the document to CB members for comments - Finalise at CB-9 | FSMed/WHO SPC CB members | N.A. |
| Renewal of PPHSN CB | Before CB-9 (Feb. 2003) | - Follow up of nominations - Seeking consensus for subregional nominations - Select the “at large” members | SPC SPC CB members | N.A. |
| Establish a revolving fund to support rapid response to outbreaks | Before Feb. 2003 | - CB committee to describe the various options - LabNet & EpiNet meetings to consider and finalise - Present to WHO/SPC HoH & Ministerial Meeting in Tonga (March 2003) for endorsment and commitment of funds - Seek complementary funding from Allied members and others | CB committee LabNet & EpiNet members WHO/SPC CB members | N.A. N.A. PPHSN Core members ? |
| Explore partnership with other Allied members | Aug. 2002 | - Send letters of invitation for expression of interest - Advocate and actively seek interest | SPC CB members | N.A. N.A. |
| Define & implement advocacy and marketing activities for PPHSN | Done Before Oct. 2002 Done | - Letter of support to SPC - Mobilise EpiNet National Focal Points to advocate the inclusion of PPHSN on the HoH & Ministers Meeting agenda (Tonga, Mar 03) - Aim at PIF Heads of States through the CROP Health & Population working group - Letter to NPHP (Australia) seeking collaboration | CB members CB core members SPC/WHO/FSMed CB members | N.A. |

| Develop LabNet procedures and enhance efficiency | Sept. 2002 Sept. 2002 Before Feb. 2003 Sept. 2002 Feb. 2003 Feb. 2003 Sept. 2002 | - Formalise L2 labs LabNet status - Establish arrangements for rapid supply of diagnostic kits & supplies - Define procedures for ordering supplies & diagnostic kits - Pursue consultation with Airlines & shipping agents - Strengthen quality assurance protocols for LabNet - Conduct a LabNet training needs assesment - Complete, report and disseminate conclusions of rapid diagnostic kits evaluation & include findings into the PPHSN guidelines | WHO SPC/WHO CB Committee SPC IPNC/PPTC IPNC/PPTC IPNC/CB members | N.A. WHO N.A. N.A. N.A. N.A. WHO/SPC/IPNC |
| --- | --- | --- | --- | --- |
| Expansion of PacNet-Restricted | Aug. 2002 | - To all EpiNet team: members Seek approval from Core members DoH & WHO offices | SPC | N.A. |
| Develop an influenza pandemic preparedness & contengency Plan | Before end 2002 | - Establish a regional influenza specialists group - Draft ToRs | SPC/WHO Coll. Centre WHO Coll. Centre | N.A. |
| Plan for CB –9 meeting | Before Feb. 2003 | - Secure funding & other resources - Prepare agenda - Send out invitations - Generate & compile working documents - Make all other administrative arrangements | SPC SPC/WHO/CB members | ? |
| Prepare for HoH & Ministers Meeting | Feb. 2003 | - Specific preparation will be dealt by at CB-9 | CB members | N.A. |
| Explore establishment of PPHSN new regional positions | On going | - Seek funding & institutional support | SPC/WHO/PPHSN Core members | ? |
| Maximise benefits of attendance to relevant regional & international meetings | Aug. 2002 Aug. 2002 May 2003 On going | - Contact PPHSN membership to encourage submission of abstracts to the CDNA Conference organisers - Letter to AusAID to seek Meeting support for PPHSN members to attend CDNA Annual Conference (April 2003) - Ensure PPHSN representation at TEPHINET Regional Meeting (SEARO/WPRO) - Advocate PPHSN at PIHOA meetings | SPC CB Chairperson NCEPH/FSMed SPC/WHO/FSMed/ PIHOA | N.A. |
| Adapt & trial revised IHR tools | Aug. 2002 | - Contact WHO HQ via WPRO and express PPHSN interest - Secure funding - Implement trial | SPC | N.A. ? ? |

| Develop PPHSN information, publication and documentation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Finalise & publish the PPHSN guidelines | Aug. 2002 Oct 2002 Dec. 2002 Feb. 2003 March 2003 Before end 2003 | - Disseminate current draft to all EpiNet team members for comments - Secure funding & select experts among EpiNet National Teams membership - Selected EpiNet members to compile comments & finalise the draft guidelines - Table the final draft guidelines to the regional EpiNet Meeting - Submit the final draft guidelines to WHO/SPC HoH & Ministerial Meeting in Tonga for advocacy & marketing - Publication & dissemination final guidelines | WHO/SPC WHO EpiNet members WHO/SPC WHO/SPC SPC | N.A. WHO WHO N.A. N.A. WHO/CDC(BT)? |
| Publication of Inform’Action issues | On going | - Encourage PPHSN members contributions - Implement all other publication-related activities | CB members SPC | N.A. SPC |
| Finalise & update the PPHSN Website | On going | - Finalise PPHSN logo - Link with the PPHSN regional CD database - Update on-line information | SPC SPC SPC/CB members | SPC N.A. SPC |
| Develop the PPHSN CDs regional database | Before Feb. 2003 On going | - CB committee to address the various tasks under the ToRs (e.g., define list of diseases, indicators & data, identify methods & ways for information dissemination & usage) - Present the outcome to the EpiNet meeting(s) - Develop health mapping capacity | CB committee CB committee CB members | N.A. N.A. ? |
| Document legislative & regulatory models for CDs S&R | On going | - Collect, compile, disseminate appropriate documentation - Post on-line documentation and disseminate otherwise | SPC SPC | N.A. |

__________________