SECRETARIAT OF THE PACIFIC COMMUNITY

8th MEETING OF THE COORDINATING BODY (CB)

Of THE PACIFIC PUBLIC HEALTH SURVEILLANCE NETWORK (PPHSN)

24 — 26 July 2002, Noumea, New Caledonia

## Annex 1 – PPHSN 12 months Plan of Action

| INITIATIVES | DATE/TIMING | ACTIVITIES | RESPONSIBILITIES | FUNDING |
| --- | --- | --- | --- | --- |
| PPHSN Meetings, workshops, training sessions |
| Organise a LabNet Meeting | Feb. 2003 (1st week) Suva, Fiji | Secure funding & other resources Identify a L2 lab for PNG Prepare agenda Send out invitations Generate & compile working documents Make all other administrative arrangements | TWB | Pending ? WHO/SPC/CDC (BioTerrorism) |
| Organise a regional EpiNet Meeting | Feb. 2003 (2nd week) Nadi/Suva, Fiji (to be explored) | Explore the various possible options with PEHI/CDC for combining Micronesian EpiNet & regional EpiNet Meeting Draft evaluation & monitoring guidelines for EpiNet teams (national & regional) Model ToRs (national & regional) Secure funding & other resources Prepare agenda Send out invitations Generate & compile working documents Make all other administrative arrangements | SPC Selected EpiNet members (ref. Guidelines) CB members WHO/SPC SPC CB members WHO/SPC | Pending ? WHO/SPC/CDC (PEHI/BT) |
| Organise a regional Consultation meeting for PPHSN training activities | Feb. 2003 Before end 2003 | Conduct training needs analysis (separate from LabNet needs) Secure funding & other resources Prepare agenda Send out invitations Generate & compile working documents Make all other administrative arrangements | EpiNet Meeting specific working group Fiji School of Medicine | Not Applicable ? ? |
| Conduct field investigation training in selected PICTs | Nov. 2002 Before end 2003 | In Micronesian PICTs In South Pacific PICTs | WHO/SPC/CB members | WHO/UNICEF WHO/UNICEF |

| PPHSN Planning and structures’ development |
| --- |
| Prepare a flexible review & update process for EpiNet teams membership (national & regional) | Before Oct. 2002 | Draft the procedure Contact EpiNet National Focal Points Identify L1 national Focal Point | SPC | N.A. |
| Develop & implement a PPHSN Strategic plan | Before Oct. 2002 | Put together the existing PPHSN planning documentation Refine Mission statement etc. Devote part of the plan to fund raising strategy, advocacy and policy framework | SPC CB members CB members | N.A. |
| Consider inclusion of NCDs in PPHSN | Before end 2002 | Prepare discussion document Circulate the document to CB members for comments Finalise at CB-9 | FSMed/WHO SPC CB members | N.A. |
| Renewal of PPHSN CB | Before CB-9 (Feb. 2003) | Follow up of nominations Seeking consensus for subregional nominations Select the “at large” members | SPC SPC CB members | N.A. |
| Establish a revolving fund to support rapid response to outbreaks | Before Feb. 2003 | CB committee to describe the various options LabNet & EpiNet meetings to consider and finalise Present to WHO/SPC HoH & Ministerial Meeting in Tonga (March 2003) for endorsment and commitment of funds Seek complementary funding from Allied members and others | CB committee LabNet & EpiNet members WHO/SPC CB members | N.A. N.A. PPHSN Core members ? |
| Explore partnership with other Allied members | Aug. 2002 | Send letters of invitation for expression of interest Advocate and actively seek interest | SPC CB members | N.A. N.A. |
| Define & implement advocacy and marketing activities for PPHSN | Done Before Oct. 2002 Done | Letter of support to SPC Mobilise EpiNet National Focal Points to advocate the inclusion of PPHSN on the HoH & Ministers Meeting agenda (Tonga, Mar 03) Aim at PIF Heads of States through the CROP Health & Population working group Letter to NPHP (Australia) seeking collaboration | CB members CB core members SPC/WHO/FSMed CB members | N.A. |

| Develop LabNet procedures and enhance efficiency | Sept. 2002 Sept. 2002 Before Feb. 2003 Sept. 2002 Feb. 2003 Feb. 2003 Sept. 2002 | Formalise L2 labs LabNet status Establish arrangements for rapid supply of diagnostic kits & supplies Define procedures for ordering supplies & diagnostic kits Pursue consultation with Airlines & shipping agents Strengthen quality assurance protocols for LabNet Conduct a LabNet training needs assesment Complete, report and disseminate conclusions of rapid diagnostic kits evaluation & include findings into the PPHSN guidelines | WHO SPC/WHO CB Committee SPC IPNC/PPTC IPNC/PPTC IPNC/CB members | N.A. WHO N.A. N.A. N.A. N.A. WHO/SPC/IPNC |
| --- | --- | --- | --- | --- |
| Expansion of PacNet-Restricted | Aug. 2002 | To all EpiNet team: members Seek approval from Core members DoH & WHO offices | SPC | N.A. |
| Develop an influenza pandemic preparedness & contengency Plan | Before end 2002 | Establish a regional influenza specialists group Draft ToRs | SPC/WHO Coll. Centre WHO Coll. Centre | N.A. |
| Plan for CB –9 meeting | Before Feb. 2003 | Secure funding & other resources Prepare agenda Send out invitations Generate & compile working documents Make all other administrative arrangements | SPC SPC/WHO/CB members | ? |
| Prepare for HoH & Ministers Meeting | Feb. 2003 | Specific preparation will be dealt by at CB-9 | CB members | N.A. |
| Explore establishment of PPHSN new regional positions | On going | Seek funding & institutional support | SPC/WHO/PPHSN Core members | ? |
| Maximise benefits of attendance to relevant regional & international meetings | Aug. 2002 Aug. 2002 May 2003 On going | Contact PPHSN membership to encourage submission of abstracts to the CDNA Conference organisers Letter to AusAID to seek Meeting support for PPHSN members to attend CDNA Annual Conference (April 2003) Ensure PPHSN representation at TEPHINET Regional Meeting (SEARO/WPRO) Advocate PPHSN at PIHOA meetings | SPC CB Chairperson NCEPH/FSMed SPC/WHO/FSMed/ PIHOA | N.A. |
| Adapt & trial revised IHR tools | Aug. 2002 | Contact WHO HQ via WPRO and express PPHSN interest Secure funding Implement trial | SPC | N.A. ? ? |

| Develop PPHSN information, publication and documentation |
| --- |
| Finalise & publish the PPHSN guidelines | Aug. 2002 Oct 2002 Dec. 2002 Feb. 2003 March 2003 Before end 2003 | Disseminate current draft to all EpiNet team members for comments Secure funding & select experts among EpiNet National Teams membership Selected EpiNet members to compile comments & finalise the draft guidelines Table the final draft guidelines to the regional EpiNet Meeting Submit the final draft guidelines to WHO/SPC HoH & Ministerial Meeting in Tonga for advocacy & marketing Publication & dissemination final guidelines | WHO/SPC WHO EpiNet members WHO/SPC WHO/SPC SPC | N.A. WHO WHO N.A. N.A. WHO/CDC(BT)? |
| Publication of Inform’Action issues | On going | Encourage PPHSN members contributions Implement all other publication-related activities | CB members SPC | N.A. SPC |
| Finalise & update the PPHSN Website | On going | Finalise PPHSN logo Link with the PPHSN regional CD database Update on-line information | SPC SPC SPC/CB members | SPC N.A. SPC |
| Develop the PPHSN CDs regional database | Before Feb. 2003 On going | CB committee to address the various tasks under the ToRs (e.g., define list of diseases, indicators & data, identify methods & ways for information dissemination & usage) Present the outcome to the EpiNet meeting(s) Develop health mapping capacity | CB committee CB committee CB members | N.A. N.A. ? |
| Document legislative & regulatory models for CDs S&R | On going | Collect, compile, disseminate appropriate documentation Post on-line documentation and disseminate otherwise | SPC SPC | N.A. |

__________________