GENERAL RECOMMENDATIONS AND PLAN OF ACTION

2ND REGIONAL EPINET WORKSHOP, 7TH -11TH JUNE 2004, SPC, NOUMEA.

#### GENERAL RECOMMENDATIONS

1. To establish and maintain strong collaboration between human and animal health services both in country and at regional level.

2. To develop and strengthen capacity on influenza surveillance in PICTs to facilitate swift detection of an outbreak, and to undertake responsibility of preparedness to influenza pandemic threat or occurrence.

3. To explore and develop feasible options for the assessment of the burden of influenza in PICTs.

4. To develop and strengthen laboratory capacities to facilitate efficient surveillance especially influenza virologic surveillance in PICTs.

5. To further develop and improve surveillance systems in the PICTs by optimising use of scarce resources for PPHSN expanded list of priority diseases.

6. To undertake training in Epidemiology to facilitate the improvement in surveillance and response to communicable disease threats and events in the Pacific Region.

7. To promote a good understanding of the new international health regulation (IHR) and related issues, and integrate IHR into the framework of the PPHSN.

8. To review and improve on the infection control measures in PICTs by establishing and formalising the Pacific regional infection control network under the umbrella of PPHSN.

9. To formalise and operationalise the Regional EpiNet team with its clear roles and functions, including funding implications, for endorsement from Health Ministers' meeting in Samoa, 2005.

### PLAN OF ACTION 2004-2006

| Activity | Measurable indicator | Means of verification | Leading agency/group | Time frame |
| --- | --- | --- | --- | --- |

| 1. To establish and maintain strong collaboration between human and animal health services both in country and at regional level |
| --- |
| Representatives from the Veterinary/animal health services are members in the National influenza pandemic taskforces/ CDCC or similar bodies. | Representatives from veterinarians or animal health services in the National influenza pandemic or national health taskforces or CDCC | Reports and attendance from minutes of meetings | National/Regional EpiNet focal points/Animal Health focal points, MOH, Animal health services | By August 04 |
| Investigate outbreaks of disease/deaths in animals, even if based on rumours only, and report to human health or EpiNet teams and communicate risks to the general public. | Number of investigations carried out based on rumours. Number of confirmed outbreaks of animal/avian influenza or other disease | Report and documentations | Animal health services, MOH (incl. National EpiNet teams), PPHSN working partners | Whenever an outbreak is suspected and investigated |
| Regional/sub regional meetings of representatives from animal and human health to address human diseases of zoonotic origin | Meetings as indicated by events in the region or globally, or proactively biennially, where both parties attended | Meeting reports | As above plus FAO, OIE, Regional Animal Health services | Whenever indicated or biennially |
| Dual postings of interest to animal and human health in PacNet and PacVet | Number of postings and/or cross postings per month | Report of postings on PacNet and PacVet | National EpiNet team and focal points for animal health, PPHSN-CB focal point and working partners | First posting by August 04 and ongoing. |

| 2. To develop and strengthen capacity on influenza surveillance in PICTs to facilitate swift detection of an outbreak, and to undertake responsibility of preparedness to influenza pandemic threat or occurrence. |
| --- |
| 2a. To strengthen early warning systems and surveillance for influenza covering both inter-pandemic and pandemic periods |
| Proactive investigations, and early reporting of clusters based on rumours, of acute fever and respiratory symptoms e.g. acute fever and cough; OR large number of animals sick or died of unknown causes. | Number of clusters identified and investigated | Reports of investigated clusters. | MOH (EpiNet teams/CDCC) and Animal health focal person(s), with PPHSN working partners | Whenever an outbreak is suspected and investigated |
| Regular feedback and risk communication from central level to those reporting from the fields. | Number of information feedback from Central to those reporting from fields and vice versa. Number of postings to Pac Net. | Number of feedback reports and reports on postings from PacNet archive | MOH (EpiNet teams/CDCC), PPHSN-CB focal point, WHO, and other working partners | Ongoing |
| 2b. To improve and strengthen Influenza- like illness (ILI) surveillance using PPHSN Influenza preparedness guidelines as references. |
| To standardize and harmonise clinical case definition (as in PPHSN Influenza Preparedness Guidelines and that of countries) | Technical assistance provided through country visits to at least five of the PICTs | Technical assistant’s country-visit reports. | MOH (EpiNet teams/CDCC), PPHSN-CB focal point, WHO and other working partners | By December 2005 |
| To support analysis and interpretation of surveillance data on ILI or similar data. | Analysis and interpretation of ILI or similar data for at least five countries. | Technical assistant ‘s country visit reports. | MOH (EpiNet teams/CDCC), PPHSN-CB focal point, WHO and other working partners | By December 2005 |
| Refer also to Section 3 |

| 2c. Countries to undertake Influenza Pandemic Preparedness Plan using PPHSN Influenza Pandemic Preparedness Guidelines and WHO Checklist as references. |
| --- |
| PPHSN influenza pandemic preparedness guidelines are compiled in close consultation with ISG and completed. | The guidelines are completed for distribution. | Copy of the guidelines | PPHSN-CB focal point with ISG | End of July 04. |
| PPHSN influenza pandemic preparedness guidelines are distributed to EpiNet teams(/CDCC) and DOH before Ministers of Health meeting in Samoa, 2005. | PPHSN influenza pandemic preparedness guidelines distributed to EpiNet teams and DOH | Distribution list | PPHSN-CB focal point | By August 2004 |
| National influenza pandemic preparedness Plan to be completed within the timeline set by country representatives during, and after the EpiNet meeting | National influenza pandemic preparedness Plan is completed within timeline, using the PPHSN influenza pandemic preparedness guidelines as well as WHO Checklist as references. | Completed document available | MOH (+EpiNet team/CDCC, Taskforces) with Animal health services. | By January 05 (latest by countries). |
| To share national influenza pandemic preparedness plan with community and other stakeholders. | Number of community meetings; multimedia awareness programs; short survey on scope of community awareness and knowledge of pandemic implications. | Reports on activities. | As above | Started in January 2005 |
| The PPHSN influenza pandemic preparedness guidelines is to be itemized in the agenda for Ministers of Health’s meeting in Samoa, 2005 | This document is included in the agenda for Health Ministers’ meeting, Samoa 2005 | Agenda for the Ministers of Health meeting. Report of the meeting. | MOH, PPHSN-CB focal point, WHO and PPHSN partners | By August 04 (itemised in Agenda) By Jan 05 (document distributed to Ministers) |
| An animal influenza component is to be part of the PPHSN influenza pandemic preparedness guideline. | The animal influenza section is incorporated in the PPHSN influenza pandemic preparedness guideline | The PPHSN influenza pandemic preparedness guideline. | SPC Vet, Regional Vet services, PPHSN-CB focal point and working partners | By July-August 04 |
| 2d. National advocacy for influenza pandemic preparedness to be scaled up accordingly. |
| To scale up advocacy via health promotion activities encouraging community participation in the pandemic preparedness plan and activities. | Number of related activities and publications produced and implemented. | Record of implemented activities and publications. | MOH, Animal health services, national EpiNet teams. | Started August 04 and ongoing |
| To link with national disaster preparedness plan and Bio-terrorism preparedness plan. | Channels of communications have been identified, established and operationalised | Inventory of established channels and reports on activities. | MOH (EpiNet teams/CDCC), and other relevant Ministries, Animal health services | By mid 2005 |
| To advocate for highest political commitment at national, regional and international levels, through Ministers of Health meeting in Samoa, 2005 | Required relevant documents are prepared for the Health Ministerial meeting in Samoa, 2005 | Meeting agenda Report of the Ministers of Health, Samoa 2005.. | As above | By January 2005 |
| 3. To explore and develop feasible options for the assessment of the burden of influenza in PICTs. |
| To undertake a retrospective 3 year-data analysis in country level for ILI or similar data; evaluate surveillance systems, and prospectively set-up ILI surveillance. | Reports of ILI or similar data analysis and interpretation from at least 3 of the PICTs per year. Contracted technical assistant. | Surveillance and Evaluation reports. | MOH (EpiNet teams/CDCC), Animal health services, PPHSN and working partners (SPC, WHO, FSMed) | By end 2005 |
| Assess impact of confirmed influenza outbreaks | Data on outbreaks are collected, collated, analysed, interpreted and disseminated. | Activity reports PacNet | As above | As an outbreak is confirmed |
| Link to 2b |

| 4. To develop and strengthen laboratory capacities to facilitate efficient surveillance especially influenza and Dengue virologic surveillance in PICTs. |
| --- |
| 4a. L1 labs to have access to rapid test kits for influenza & dengue (outbreaks) |
| Identify and prioritise national L1 labs to gain access to test supply for confirming outbreaks of influenza. | List of national priority laboratories in (L1) for supply of necessary test kits | Prioritised L1 lab list List of labs supplied tests | LabNet technical working body (TWB) and working partners, National laboratories/ LabNet focal points | By mid 2005 |
| Develop and maintain procurement channels for dengue rapid test kits. | Supply procured upon request from countries. | List of tests supplied to labs | As above | Ongoing |
| 4b. L2 labs to have Immunofluroscent microscopy capacity at least for influenza |
| Identify funding and procure supply and equipments to identified L2 labs | Funds available. Procurements of supplies for identified L2 laboratories | Activity report including expenditure and supplies. | LabNet TWB and working partners. | By end 2006 |
| 4c. L2 labs to have ELISA testing for dengue |
| Identify funding and procure supply and equipments upon L2 requests. | Funds available. Procurements of supplies for L2 labs | Activity report including expenditure and supplies. | LabNet TWB and working partners. | By mid 2005 |
| 4d. Countries with L2 labs to establish or continue sentinel ILI and virologic surveillance |
| Training of human resource to use test kits/equipments and for maintenance purposes | At least two trainings conducted within time frame of this recommendation/Action Plan | Activity reports: number of training s done; and number of people trained. | Institute Pasteur, LTWG and working partners (PPTC, WHO Coll. Lab.) | By end 2006 |
| Ensure total quality management system (TQMS); quality assurance (QA), quality control (QC) and quality improvement (QI) including safety procedures are in place. | At least two lab assessments and training sessions are carried out for L2, and at least one for L1, within the set time frame Biosafety provisions and protocols in place. | Training report List of labs with protocols and bio-security provisions | LabNet TWB especially WHO with PPTC, WHO coll. labs, and other working partners | By end 2006 |
| 5. To further develop and improve surveillance systems in the PICTs by optimising use of scarce resources for PPHSN expanded list of priority diseases. |
| 5a. Dengue Fever |
| To integrate findings based on best practice for surveillance and research (vector/clinical/laboratory) into the PPHSN framework and guidelines. | Best practices identified Contextually appropriate evidence integrated into national dengue control programs of at least 3 PICTs | Reports or publications on best practice Reports on number of countries integrating best evidence | National EpiNet teams, MOH, PPHSN CB focal point & WHO, working partners | Ongoing |
| To continue vigilance in awareness program, and enforce public health interventions on dengue fever control programs in view of DEN-3 threat to PICTs. | Frequency of relevant messages on PacNet and risks communication to PH and EpiNet teams | PacNet: number of messages & relevance of content Inform Action | MOH, PPHSN working partners | Ongoing |
| PPHSN Dengue Fever Guideline completed peer reviewed, published and distributed to PICTs. | PPHSN Guideline on Dengue Fever finalized, published and distributed | Guidelines Distribution List | WHO & PPHSNCB focal point (and working partners). | By end of 2004 |
| Dengue Fever Guidelines adapted and implemented at national level | National Guideline in 5 PICTs | Copies of guidelines | MOH (EpiNet teams/CDCC) | End of 2006 |
| Seek and identify funding for regional and national dengue fever programs | Funding Proposal Accepted Prioritise 2 national dengue control programs for funding assistance | Report on funding and prioritised countries | MOH, WHO & PPHSN working partners. | Ongoing |
| 5b. Acute flaccid paralysis (AFP) and acute fever and rash (AFR) surveillance is to be supported within the framework of PPHSN |
| Develop procedures and trial runs for email communication for hospital based active surveillance. | Procedures and trial runs documents | Copy of document & Reports | WHO (EPI), UNICEF, MOH (EpiNet teams/CDCC), PPHSN-CB focal point and working partners. | By end of 2005 |

| Select pilot countries for the trial run and train appropriate health workers | Training document Clinicians, nurses and relevant health care workers (HCW) trained in at least 3 countries. | Report on training Communication with health workers | WHO (EPI), UNICEF, MOH, EpiNet teams, PPHSN focal point and working partners. | By mid of 2005 |
| --- | --- | --- | --- | --- |
| Implemented trial results fed back to PPHSN for wider application. | Number of reports. Cases and suspected cases of AFP&AFR identified, diagnosed, reported | Reporting system | As above | By Mid 2005 |
| 5c. To support HIV /STI Surveillance under the PPHSN framework |
| To integrate current HIV/STI surveillance research in the region into the activities of the PPHSN EpiNet (and LabNet) teams in order to optimise scarce resources for surveillance programs | Number of HIV surveillance teams, which directly involve EpiNet (and LabNet) team members in-country in both routine surveillance and surveys. | Surveillance and survey reports | MOH (& EpiNet teams/CDCC), SPC HIV/STI surveillance team, Pacific STI/HIV Strategic group, WHO, GFATM, PPHSN and working partners | By 2006 |
| To increase capacity of PICTs to undertake HIV surveillance. | Number of new HIV/STI projects developed and or implemented by PICTs and involving Pacific health professionals and PHTI. | Project and surveillance reports | As above | As above |
| 5d. To develop appropriate linkages with food safety and improve surveillance for food-borne diseases under the PPHSN framework. |
| Activate and operationalise food borne disease surveillance working group (FBDSWG) | FBDWG active and functional/ No. of meetings/ teleconferences/frequency of email exchange | Meeting reports/messages | Working group (FBDSWG) | End of 2004 |
| Develop appropriate linkages with and between groups interested in food safety | Linkages established at national and regional levels with other groups/agencies interested in food safety e.g. Codex committee, Animal health services, and other interested parties. | Reports/ Organisational charts | FBDSWG (including SPC, FAO, WHO) MOH & other national ministries | By 2006 |
| Assess capacity (clinical, laboratory, flexibility of surveillance system etc) existing within countries to undertake food borne disease surveillance | Country capacity for FBD surveillance report available for at least 3 pilot countries (clinical, lab, and Flexibility of the surveillance system | Reports | FBDSWG with Health training Institutions (FSMed) | End of 2005 |
| Facilitate conduct of food borne burden of illness study and also undertake aetiological study. | Report of studies conducted for at least 3 countries and evidence of surveillance system available to review. | Reports | As above | End of 2006 |
| 6. To undertake training in Epidemiology to facilitate the improvement in surveillance and response to communicable disease threats and events in the Pacific Region. |
| Workforce plans are in line with the implementation of the new IHR, in terms of adequate and appropriate local capacity to respond to epidemics (EpiNet or CDC teams) including those epidemics which are of international significance. | Training needs Analysis (TNA) and Workforce plan as related to new IHR implementation and Field epidemiology in PICTs- surveillance & outbreak investigation. EpiNet teams training requirements outlined Curriculum discussions, reviews& communications | TNA Document Workforce planning document Reports on communications | MOH with PHTI (FSMed), NHTI, WHO, PPHSN-CB focal point and other working partners, | By end 2006 |
| Explore inclusion of applied epidemiology training in curriculum for training of pre-service and in-service health/field workers through dialogue with Pacific regional and national health training institutions. | No. of institutions visited for consultation/or to discuss the details of the issues. | Reports | PHTI, NHTI, PPHSN-CB focal point, WHO. | By end 2005. |
| To deliver accredited short training especially short courses in addition to exploring other flexible learning possibilities | No. of short course delivered, and number of courses accredited. | Training and Accreditation report | PHTI, NHTI, PPHSN-CB focal point, WHO (with POLHN) | Ongoing |
| To facilitate development and delivery of Data for Decision Making (DDM) training | Sessions of teaching and numbers of DDM cohorts or students commenced /completed training. | Reports | PPHSN CB focal point, FSMed, CDC, PIHOA | Ongoing |
| To facilitate linkages for specialist epidemiology training in the region through Pacific Institutions | At-least two Pacific trainees on the program of FSMed, Funding & attachment at SPC-PH, Specialist centre e.g. WHO collaborating centre | Training report | Training institutions and PPHSN partners and donors | End of 2005 |
| 7. To promote a good understanding of the new international health regulation (IHR) and related issues, and integrate IHR into the framework of the PPHSN. |
| 7a: The implementation of the new IHR is to be incorporated under the PPHSN framework. |
| The Working group identified by the CB should discuss further IHR implementation issues for PICTs | CB Working group carried out teleconference- meeting reports. Implementation strategy discussed | Reports and minutes | Technical working group of PPHSN-CB, MOH | August 2004 and ongoing. |
| Communication channels and algorithms to enhance notification are established and endorsed by PICTs | Communication and notification channels established or mapped out | Reports or documents | Technical working group of PPHSN-CB, MOH | January 05 and ongoing |
| Capacity development of Public Health laboratories in the region in conjunction with surveillance activities (L2) | Capacity needs identified and addressed in conjunction with L2 surveillance development strategy. | Development report | PPHSN and partners including donors, L2 lab managers and staff, MOH. | By end 2005 |
| New IHR are endorsed by MOH. | Endorsement of new IHR by MOH | Endorsement document/report. | WHO | Nov 2004 -March 2005 |
| Capacity building: requirements Identified per Country: see section 6 Training of EpiNet teams Training of border control officers Establish and operationalise RET: see section. 9 | TNA & Training plan (or List of training) (At least 10 members of EpiNet teams from different countries and 10 border control personnel undertake short training from PIC training institutions and PHTI) – one per year | Training plan and Training reports | WHO, PPHSN CB focal point and working partners, MOH, and IHR focal point), PHTI | Ongoing |
| 7b: To prepare a document on the implications of the new IHR and its requirements including the above issues (7a&7b,) to be presented and approved at the Ministers of Health's meeting in Samoa, 2005. |
| Document written and shared as widely as possible (Revolving Funding issue is to be incorporated into document to Regional MOH's meeting in Samoa), approved at MOH meeting in Samoa | The document is ready following reasonable feedback from PICTs for presentation at the MOH meeting Document presented and endorsed at Samoa MoH meeting | Document copy Communications with PICTs Samoa MoH meeting report | PPHSN-CB, WHO with MOH & IHR focal points. | By January 2005. |
| 8. To review and improve on the infection control measures in PICTs by establishing and formalising the Pacific regional infection control network under the umbrella of PPHSN. |
| Formalise members and operationalise the Pacific regional infection control network (PICNet) under the umbrella of PPHSN | List of PICNet members is finalised and formalised. PICNet is operationalised under PPHSN umbrella. Funding is identified to support PICNET development PICNet members have teleconference meeting(s). | On PPHSN website: list of PICNet members, PICNet TOR Funding proposal/report Reports and number of teleconferences, and communications | PPHSN-CB, WHO (and working partners), EpiNet teams, other PICNet members | October 2004 and ongoing |
| Assess capacity on infection control in PICTs, and identify training needs. | Capacity assessment and training needs identified in at least 5 PICTs completed | Reports | MOH, PICNet, PPHSN-CB focal point and working partners (WHO, FSMed?) | By end of 2005 |
| In country and/or Regional training based on needs and findings. | Training conducted in at least 5 countries. Minimum standard for infection control in PICTs is set. | Reports on trainings, including minimum set for infection control standards. | PPHSN-CB focal point and working partners, PICNet, FSMed, WHO | By mid 2006 |
| Develop a PPHSN Infection Control Guideline | PPHSN Guideline on Infection control in place (APW or technical assistant to undertake) | Document ready and distributed to PICTs. | WHO, PPHSN-CB focal point and other working partners | June2005 |
| 9. To formalise and operationalise the Regional EpiNet team with its clear roles and functions, including funding implications, for endorsement from Health Ministers' meeting in Samoa, 2005. |
| In close consultation with PICTs: List of RET members including their roles, responsibilities and TOR. document on RET including revolving funding issues for submission for endorsement by Regional Minister of Health’s meeting in Samoa 2005. | RET members with its TORs finalised. The document is ready for submission to Ministers' meeting in Samoa, 2005. | RET list and TORs on PPHSN website Agenda of the Ministers of Health meeting, 2005. | PPHSN-CB, with MOH (EpiNet teams/CDCC) | By October 04 January 05 (for document for the Minister's meeting) |

ABBREVIATIONS

CDCC		Communicable disease control and prevention committee

DOH		Director(s) of Health

DDM		Data for decision making

FAO		Food and Agriculture Organisation

FBDSWG	Food borne disease surveillance working group

FSMed		Fiji School of Medicine

GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria

IHR		International Health Regulations

ILI		Influenza like illness

LabNet TWB	LabNet technical working body

MOH		Ministry(ies) of Health

NHTI		National Health training institution

OIE		World Animal Health Organisation

PHTI		Pacific Health Training Institute

PICTs		Pacific island countries and territories

PIHOA		Pacific Islands Health Officers Association

PICNet		Pacific Regional Infection Control Network

POLHN	Pacific Open Learning Health Network

PPHSN		Pacific Public Health Surveillance Network

PPHSN-CB	Pacific Public Health Surveillance Network Coordinating Body

PPTC		Pacific Paramedical Training Centre

RET		Regional EpiNet team

SPC-PHP	Secretariat of Pacific Community – Public Health Programme

STI/HIV	Sexually transmitted infections and Human Immunodeficiency Virus (infections)

TNA		Training Needs Analysis

TOR		Terms of reference

UNICEF	United Nation Children’s Fund

WHO		World Health Organisation